## Sheet1
Date | Day | Task 1 | Task 2 | Task 3 | Task 4
2018-04-23 | Monday | Mockup to Ian | Build 2 week calendar | Finish Scraping route IDs
2018-04-24 | Tuesday | Get EC2 scraper dumping into MongoDB | Build model with toy (ramp up to 1000 routes) dataset
2018-04-25 | Wednesday | Deliver Rest endpoints to Ian | Keep an eye on data collection | Do more EDA
2018-04-26 | Thursday | Finalize Data collection | Work on data cleaning/ architecture | Run model on full dataset
2018-04-27 | Friday | Begin working on app/ filtering aspect | Finish initial version of recommender model (IE full matrix)
2018-04-28 | Saturday
2018-04-29 | Sunday
2018-04-30 | Monday | Work on NLP aspect (determine 'Keywords') | Map Keywords to routes for piping
2018-05-01 | Tuesday | continue working on app
2018-05-02 | Wednesday | Start factoring code and working on powerpoint | Finish App
2018-05-03 | Thursday | Finish power point presentation
2018-05-04 | Friday